## Sheet1
USER STORY #1: Basic Overview | Joseph Bain
Getting keys and Getting situated with API's and coding environments | 8-10 hours
Creating a web UI that we can place features of our app into. Connecting the front end to the back end | 6-8 hours
Setting up OAuth so that users will be able to log in | 4-6 hours
Letting the app ask for photos for users to upload | 3-4 hours
Using google vision API to collect relevant data from uploaded content | 4-6 hours
Bringing that data to the Genius API and creating a relevant playlist based on the data | 4-6 hours
Using the playlist given by the Genius API, getting songs from the Spotify API into a playlist that the user can use | 4-6 hours